PROJECT COMPLETION REPORT

Obsolete Pesticides Cleanup  Project in Salyan, Azerbaijan

# Project Details

| Location | Salyan, Azerbaijan |
| --- | --- |
| Contaminants | DDT, Polydofen, Granozan, Zineb, and HCH |
| Project Duration | January-November 2017 |
| Project Cost | $50,000 provided by UNIDO/EC, $3,000 from Trust for Mutual Understanding, and $100,000 of co-financing provided by the government of Azerbaijan. |
| Implementing Partners | Pure Earth/Blacksmith Institute, Jianji Toxic Waste Storage and Azerbaijan Ministry of Agriculture, with additional funding from the European Commission/UNIDO, Trust for Mutual Understanding, and Government of Azerbaijan. |
| Affected Population | 2000 people |

## Background and Scope

The town of Salyan is located in south-western Azerbaijan. The contaminated site was a former pesticide and fertilizer storage facility that is now in possession of a commercial company and used for storing food. The former pesticide storage building was demolished in 1990 and pesticides that were stored there were just left exposed on the ground.

The main contaminants found at the site were: DDT, Polydofen, Granozan, Zineb, and HCH.   The area is used for storing food. Access of general public to the site was limited by the property owner. Some of the pesticides found were liquid stored in old barrels and some were solid (powder) stored in bags. The top soil at the site was also contaminated.

The cleanup project involved removing solid and liquid of obsolete pesticides (OP) and placing them in Jianji Toxic Waste Storage (Polygon).

## Danger to Public Health

Exposure to pesticides can affect the reproductive system, causing infertility, miscarriage in early stages of pregnancy, spontaneous abortions and fetal deaths. Many pesticides are known to cause cancer. The impact on human health and environment depends as much on the type of pesticide as on the level of exposure.

The families living nearby complained of headaches and DDT smell. The primary routes of exposure to pesticides for residents Salyan were: inhalation of toxic vapors, accidental ingestion of contaminated dust and soil.

## Solution Implemented

The Salyan cleanup project was prepared in January-October 2017 and implemented in November 2017

The main contaminants at the site were DDT, Polydofen, Zineb, HCH and Granozan.  During the project, 25 drums of Polydophen (110 l each) and 380 m3 of obsolete pesticides were transported to the Jianji Polygon facility for permanent waste storage. Heavy machinery – trucks and excavator were used for loading and transporting contaminated soil and pesticides.

Figure 1. Workers loading empty drums onto the truck for transportation to the hazardous waste facility

At the end of the remediation, a total of 49 trucks were sent to the Hazardous Waste Facility, of those, 2 truck were filled with nearly 500 empty drums, 2 trucks were filled with Polydaphen with total of 25 drums, 44 trucks, each 10 m3, were filled with empty drums, contaminated soil, DDT and Granozan. The pesticides were repacked in brand new FIBCs and steel drums at the Hazardous Waste Facility. Solid waste contaminated with OPs was packaged in FIBCs.

All of the collected soil and barrels were brought to a hazardous waste facility situated away from any residential areas. They were placed in 14 concrete lined pits and covered with concrete slabs on the top. Barrels with liquid pesticides were overpacked in plastic.

## Bodies Implementing the Remediation

Salyan was one of the most contaminated obsolete pesticide sites in the Former Soviet Union and perhaps the most contaminated pesticide site in Azerbiajan. In addition to Pure Earth staff, this project involved local and state government officials, the operators of the hazardous waste facility and nnumerous other local actors.

## Recommendations and Lessons Learned

After many meetings with national high ranking officials conducted by Rovshan Abbasov (Pure Earth country coordinator) the government agreed to help and provide in-kind contributions to co-finance the cleanup. This is an example of successful relationship building with the national government and has made the project a success.

## Project Result

This project was successful in cleaning up one of the largest former pesticide storage facilities in Azerbaijan from obsolete pesticides, mainly Lindane and DDT. The pesticides and contaminated soil were repackaged and transported to a specially designated hazardous waste facility.